## Contractor Tracker
41 Paquin Road – Contractor Due Diligence Tracker
Report as of July 20, 2026
Assumption: | GST Rate | 5% | (applied where a contractor's exact tax wasn't stated)
Contractor | Scope of Work | Contact | Phone / Email | Quote – Low (Pre-Tax, $) | Quote – High (Pre-Tax, $) | Disbursements / Other Fees ($) | Est. Total – Low ($, incl. GST) | Est. Total – High ($, incl. GST) | Proposed / Confirmed Date | Status | Notes / Flags
Transcona Roofing | Commercial roof inspection | Jackelynn Payne | 204-806-1517 | 795 | 795 |  | 834.75 | 834.75 | Jul 14 (completed) — DISPUTED | Invoiced Dispute Resolved | Invoice #3513 due today (Jul 20), terms Due Upon Receipt. Princely disputed authorization for this inspection the same day — do not pay until resolved.
MCW Consultants | Mechanical/electrical engineering review | Elliott Garfinkel / Cam Dahl | ext. 237 | 6800 | 10000 |  | 7140 | 10500 | TBD (avail. ≈ 2 wks from Jul 6) | Range Given – Final Fee Pending | Estimated range excludes tax and disbursements (final fee depends on building size/complexity). Cam Dahl was to confirm the final fee and scheduling — no update received since Jul 10.
HLC Consulting (Phase I ESA) | Environmental Site Assessment (CSA Z768-01) | Nathan Moschler | 204-290-1031 | 3700 | 3700 |  | 3885 | 3885 | Proposed Jul 23 PM or Jul 24 AM | Proposal Received – Unsigned | Fee includes an assumed $1,000 3rd-party ERIS search cost. Extra reliance letters are $450 each. Requires signed 'Agreement for Environmental Services' returned to Leo Camirand.
Barnes & Duncan | Building Location Certificate + Additional Features | Avery Bowen / Christian Korell | 204-284-5999 | 2950 | 2950 | 53 | 3150.5 | 3150.5 | Fieldwork starts 5 business days after authorization | Estimate Received – Unsigned | SCOPE FLAG: this covers a Building Location Certificate only — narrower than the boundary/easement/encroachment survey originally requested. Confirm scope before signing. Quote valid 30 days (≈ Aug 13).
Jilmark Construction | Design-build / GC pricing | David Regehr-Wiens | [6 empty] | Confirmed Jul 24, 9:30-11am | No Fee required | No fee yet; pending their review of site drawings/documents. Confirm whether the Jul 16 site visit actually took place, and request the fee.
Castle Pest Control | Pest inspection & program plan | James Girden | 431-999-2402 | [5 empty] | Proposed Jul 24, 10am | No Fee required | Confirm whether the Jul 13 visit occurred; no quote received either way.
Air-Rite Inc | HVAC, refrigeration & kitchen equipment review | Ben Hueging | [6 empty] | TBD — awaiting our reply | Awaiting Scope Answers | Ben (back from vacation Jul 15) asked whether the plant is operating and for the exact scope of the review; said probably not until 'next week'. Needs a reply from our side.
Parsus Engineering | Facility/process engineering review (CFIA readiness) | Alex Korotkov / Jesse Nugent | [6 empty] | TBD — awaiting callback | Awaiting Callback | Jesse Nugent (Sr. Mechanical/Process Engineer) tried calling Richard back on Jul 16 (204-336-6637) — call has not been returned yet.
Phillips & Stevens | Survey certificate | Wilson Phillips | [6 empty] | TBD — no response | No Response | Drawings and address sent Jul 10; no reply since on availability or fee.
Beach Rocke Engineering | Structural engineering assessment | Roman Hudon | [6 empty] | N/A | Declined | Declined twice: first cited project timing, then said the building was too large for their office to take on.
TOTAL — Quotes Received | [6 empty] | 15010.25 | 18370.25
Status Key:
Quote / proposal / estimate received
In progress — awaiting a response
Stalled — no response, or date passed unconfirmed
Needs attention — declined, or disputed/urgent
Note on C3: Manitoba GST assumption used to estimate totals where a contractor quoted a pre-tax fee. Confirmed exact on Transcona's invoice (5%). Edit this cell to recalculate every estimated total below.

## Sheet1
Contractor | Scope of Work | Contact
Transcona Roofing | Commercial roof inspection | Jackelynn Payne
MCW Consultants | Mechanical/electrical engineering review | Elliott Garfinkel / Cam Dahl
HLC Consulting (PCA) | Property Condition Assessment (ASTM E2018-24) | Nathan Moschler
HLC Consulting (Phase I ESA) | Environmental Site Assessment (CSA Z768-01) | Nathan Moschler
Barnes & Duncan | Building Location Certificate + Additional Features | Avery Bowen / Christian Korell
Jilmark Construction | Design-build / GC pricing | David Regehr-Wiens
Castle Pest Control | Pest inspection & program plan | James Girden
Air-Rite Inc | HVAC, refrigeration & kitchen equipment review | Ben Hueging
Parsus Engineering | Facility/process engineering review (CFIA readiness) | Alex Korotkov / Jesse Nugent
Phillips & Stevens | Survey certificate | Wilson Phillips
Beach Rocke Engineering | Structural engineering assessment | Roman Hudon
Contractor | Scope of Work
Jilmark Construction | Design-build / GC pricing
Castle Pest Control | Pest inspection & program plan
Air-Rite Inc | HVAC, refrigeration & kitchen equipment review