# EQUIPMENT SOURCING & PROCUREMENT REPORT

China-Direct (Alibaba) Sourcing — 1,000,000 Meals/Day RTE Facility

Shelly's Indigenous Bistro Ltd. • Prepared by: Princely Eleazu, Shelly’s Bistro. • Revision 2 — July 20, 2026

# 1. Purpose & What Changed

Revision 1 of this report replaced all suppliers with maximum-capacity single machines from Alibaba. Management has since met the production target: 1,000,000 ready-to-eat meals per day. No single food machine on any market — Chinese or European — processes that volume alone, so this revision re-sizes the plant as a MULTI-UNIT PARALLEL-LINE operation: the same verified China suppliers, but with the correct number of machines per category to hit the target with redundancy.

# 2. Capacity Model — 1,000,000 Meals/Day

All machine counts in this report derive from the model below. Two assumptions (meal weight and product mix) materially move the counts and must be confirmed against the actual menu.

| Parameter | Value | Basis |
| --- | --- | --- |
| Daily output | 1,000,000 meals/day | Management production target |
| Average meal weight | 450 g | Multi-component RTE tray assumption - confirm against menu |
| Daily tonnage | 450 t/day finished product | 1M x 450 g |
| Operating window | 20 hr/day production + 4 hr sanitation | 3-shift industrial pattern |
| Effective hours (85% OEE) | 17 hr/day | Industry-standard availability x performance x quality |
| Plant instantaneous rate | ~26,500 kg/hr | 450,000 kg / 17 hr |
| Packaging closure rate | ~980 packs/min sustained | 1,000,000 / (17 x 60) |
| Product mix (tonnage) | Protein 30% - Root veg 15% - Potato 10% - Leafy 10% - Rice/grains 15% - Soup/sauce 15% - Fruit 5% | Multi-product RTE assumption - re-run model when menu is fixed |
| Pack format mix | Trays 70% (~690/min) - Cups 20% (~200/min) - Other 10% | Assumption - re-run when pack formats fixed |

Sizing rule: each line is sized to its share of the 26,500 kg/hr plant rate, then rounded UP with at least one redundant unit on continuously running lines (an N+1 approach). At this scale a single machine failure without a spare stops roughly 50,000-200,000 meals of daily output.

# 3. Executive Summary

- Fleet: 64 machines across 22 categories (vs 22 single machines in Revision 1). Packaging is the dominant constraint: ~980 packs/min sustained requires 6 MAP tray sealers and 4 rotary cup lines running in parallel.

- Equipment FOB China: ~USD $689K (~CA$930K). Total project including freight, compliance, installation and 15% contingency: ~CA$1.6-1.8M.

- Same supplier base as Revision 1 — every supplier is a verified Alibaba manufacturer; multi-unit orders (2-6 units per category) create significant negotiating leverage and justify factory-direct pricing below listed FOB.

- Timeline: staged delivery over 4-6 months. SPE-1000 field evaluation of 64 machines is the critical path — book Inspection & Technical Services Manitoba capacity NOW, before any PO.

- Honest flag: at 1M meals/day, this equipment scope is only one workstream. Building services (power — est. 2-4 MW, steam, refrigeration, waste water), cold-chain warehousing, and 450 t/day of outbound logistics are outside this report and larger than the equipment budget.

# 4. Master Equipment Register — Multi-Unit Fleet

Unit capacities and FOB prices are from live Alibaba listings (verified July 2026, links in the research annex). Required rates come from the Section 2 model. Extended FOB uses listing midpoints; quote items use engineering estimates pending RFQ.

| # | Line | China Supplier (Alibaba) | Unit Capacity | Required Rate | Qty | Unit FOB (USD) | Ext. FOB |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Meat slicer/flaker | Zhengzhou Beres Machinery (Henan) | 6,000 kg/hr | 4,765 kg/hr | 2 | $2,299-4,000 | $6,300 |
| 2 | Meat dicer | Chengdu Vleda Star (Sichuan) - Verified | 3,000 kg/hr | 3,176 kg/hr | 2 | $7,800-8,385 | $16,200 |
| 3 | Root veg wash + peel | Jiaozuo Zhoufeng (Henan) - 13 yrs | 2,000 kg/hr | 3,971 kg/hr | 2 | ~$2,000 | $4,000 |
| 4 | Root veg multi-cutter | Saidashi Machinery (Henan) | 2,500 kg/hr | 1,588 kg/hr | 1 | $3,365 | $3,365 |
| 5 | Root veg slicer | Shandong Xinlongjia (Shandong) | 3,000 kg/hr | 1,191 kg/hr | 1 | ~$3,500 | $3,500 |
| 6 | Root veg dicer | Shandong Dongsheng (Shandong) | 3,000-5,000 kg/hr | 1,191 kg/hr | 1 | Quote ~$17,500 | $17,500 |
| 7 | Leafy veg washer | Zhaoqing Fengxiang (Guangdong) - 17 yrs | 3,000 kg/hr | 2,647 kg/hr | 2 | $1,500-3,370 | $4,870 |
| 8 | Leafy veg cutter | Zhucheng Dayang (Shandong) - 5 yrs | 2,000 kg/hr | 2,647 kg/hr | 2 | $1,200-4,000 | $5,200 |
| 9 | Leafy centrifugal dryer | Shandong Leading (Shandong) - 10 yrs | 1,500 kg/hr | 2,647 kg/hr | 2 | $17,600-22,000 | $39,600 |
| 10 | Potato peel + wash line | Zibo Taibo Industrial (Shandong) | 3,000 kg/hr | 2,647 kg/hr | 1 | Quote ~$20,000/line | $20,000 |
| 11 | Fruit peel/cut | Henan Vic Machinery (Henan) - 13 yrs | 1,500 kg/hr | 1,324 kg/hr | 1 | ~$6,200 | $6,200 |
| 12 | Rice multihead weighers | Guangdong Kenwei (Guangdong) - 18 yrs | 120 packs/min | 245 packs/min | 3 | ~$14,000 | $42,000 |
| 13 | Soup fillers (hot, chunks) | Guangdong Rifu (Guangdong) - Verified | 133 packs/min | 196 packs/min | 2 | $15,000-20,000 | $35,000 |
| 14 | Sauce fillers (servo) | Shanghai Npack (Shanghai) - 15 yrs | 100 packs/min | 147 packs/min | 2 | ~$15,000 | $30,000 |
| 15 | Salad multihead weighers | Guangdong Kenwei (Guangdong) - 18 yrs | 80 packs/min | 98 packs/min | 2 | ~$30,000 | $60,000 |
| 16 | Noodle multihead weighers | Guangdong Kenwei (Guangdong) - 18 yrs | 60 packs/min | 98 packs/min | 2 | ~$17,000 | $34,000 |
| 17 | MAP tray sealers | Guangzhou Fuhe (Guangdong) - 16 yrs | 140 trays/min | ~690 trays/min | 6 | ~$34,000 | $204,000 |
| 18 | Rotary cup fill-seal | Wenzhou Crownchi (Zhejiang) - 8 yrs | 60 cups/min | ~200 cups/min | 4 | ~$11,000 | $44,000 |
| 19 | Tunnel ovens (patties) | Henan Gondor (Henan) - 5 yrs | 2,000 kg/hr | 3,970 kg/hr | 2 | $8,499-18,499 | $27,000 |
| 20 | Pressure cookers 1,000 L | Shandong Longze (Shandong) - 12 yrs | ~470 kg/hr each | 2,382 kg/hr | 6 | $7,500-8,000 | $46,500 |
| 21 | Jacketed kettles 1,000 L | Shandong Hede (Shandong) - 6 yrs | ~500 kg/hr each | 1,588 kg/hr | 4 | $650-2,930 | $7,160 |
| 22 | Metal detectors (CCP) | JunHong Electronic (Guangdong) - 20 yrs | 1 per lane | 12 lanes + 2 spare | 14 | ~$2,300 | $32,200 |

Notes: (1) Tray sealing at ~690 trays/min is intentionally spread across 6 x 140 trays/min machines rather than fewer larger units — parallel redundancy on the bottleneck. (2) Pressure cookers and kettles are batch vessels; counts assume ~45-min cycles at 1,000 L. (3) One metal detector per packaging lane (12 lanes) plus 2 spares — CCPs are never shared between lines. (4) Thermal/cooking capacity should be re-validated against the final menu: if more than ~35% of tonnage is cooked product, add continuous cooking lines.

# 5. Budget Summary

| Item | Estimate | Notes |
| --- | --- | --- |
| Equipment FOB China (64 machines) | USD ~$689K (~CA$930K) | Extended prices, Section 4; quote items at estimate |
| Freight + insurance + customs + inland rail | CA$220-320K | 10-14 x 40ft containers, Vancouver + rail to Winnipeg; validate with forwarder |
| SPE-1000 field evaluation (64 machines) | CA$51-96K | CA$800-1,500 per machine, Inspection & Technical Services Manitoba |
| CRN registration (10 pressure vessels) | CA$30-50K | 6 cookers + 4 kettles; ASME stamp required |
| Installation & commissioning | CA$120-180K | ~12-15% of equipment for multi-line integration |
| Contingency (15%) | CA$210-240K | Remediation, spares, price variance |
| TOTAL PROJECT (equipment scope) | CA$1.6-1.8M | vs CA$2.9M+ single-line premium plan at 1/20th this capacity |

For context: the original premium-channel plan (CA$2.9M landed) bought a plant rated at roughly 40-60,000 meals/day. This China-direct fleet targets 20x that output at roughly 60% of the cost — the trade-offs are certification work, remote service, and the compliance program in Section 6.

# 6. Compliance at Fleet Scale

- SPE-1000: all 64 machines require field evaluation by Inspection & Technical Services Manitoba (CA$800-1,500 each, CA$51-96K total). Mitigate by standardizing electrical specs across the fleet — identical panels on identical units evaluate faster — and mandating CSA-recognized components (breakers, contactors, VFDs) in every PO.

- CRN: 10 pressure vessels (6 cookers + 4 kettles) need Canadian Registration Numbers with ASME-stamped vessels — CA$30-50K and 4-6 weeks; start the paperwork at PO placement.

- CFIA: at 1M meals/day the facility is a federally licensed establishment under the Safe Food for Canadians Regulations with a full preventive-control plan; engage CFIA early — equipment sanitary design evidence (SUS304/316 certificates, continuous welds) must be in every PO.

- HACCP: 14 metal detectors as CCPs, one per lane, with test-piece certificates and calibration documentation shipped with each unit.

# 7. Virtual Factory Viewing Schedule

Remote inspection replaces in-person visits. Winnipeg (CDT) is 13 hours behind China Standard Time; the practical live window is 7:00-9:30 PM Winnipeg = 9:00-11:30 AM next morning in China. At this order volume (~CA$935K FOB), suppliers will accommodate any reasonable demonstration request — use that leverage.

| When | Activity | Detail | Timing / Notes |
| --- | --- | --- | --- |
| Week 1 | RFQs + capacity evidence | Send RFQs via Alibaba Trade Assurance to all suppliers with the REQUIRED RATE per line (Section 4) - not just model numbers. Demand rated-throughput test reports, electrical drawings (600V/3-phase 60Hz), and factory videos. Disqualify any factory that cannot evidence the rate. | Async - no live calls |
| Week 2 | Cluster 1 live tours - Shandong & Henan | Live video factory tours: Weifang/Zhucheng/Zibo cluster (Xinlongjia, Dayang, Leading, Longze, Hede, Taibo) and Zhengzhou/Jiaozuo cluster (Beres, Saidashi, Vic, Gondor, Zhoufeng). 2-3 tours per evening. | Winnipeg 7:00-9:30 PM = China 9:00-11:30 AM next day |
| Week 3 | Cluster 2 live tours - Guangdong & East | Live video tours: Zhongshan/Guangzhou/Dongguan/Zhaoqing cluster (Kenwei, Rifu, Fuhe, JunHong, Fengxiang) plus Shanghai Npack, Chengdu Vleda, Wenzhou Crownchi. | Winnipeg 7:00-9:30 PM = China 9:00-11:30 AM next day |
| Week 3-4 | Full-rate demos at scale | Each factory runs YOUR product at the FULL required rate on camera for a sustained 30-60 min window, output weighed on camera. At 1M meals/day there is zero headroom for optimistic capacity claims. | 45-90 min per machine |
| Week 4-5 | Commercial close | Negotiate multi-unit pricing (2-6 units per category = real leverage), warranty, spare-parts packages, and staggered delivery. Place POs through Trade Assurance. | Async + 2-3 live calls |
| Pre-shipment | Third-party inspection + video FAT | SGS / Bureau Veritas / TUV pre-shipment inspection at each cluster (~US$300-500/man-day); attend every FAT by live video: full-rate run, safety interlocks, panel components, nameplates filmed. | 2-3 inspection days per cluster |

## 7.1 Best Practices (fleet-scale additions)

- Live walkthroughs only — continuous camera through the factory floor, welding stations, CNC area and warehouse to verify manufacturer status (not a trading company). Verify the business license on camera against the Alibaba storefront name.

- Sustained full-rate demos: 30-60 minutes at the required rate with output weighed on camera — short burst demos hide thermal drift, jam rates and real OEE.

- For multi-unit orders, require serial-numbered FATs for EVERY unit, not just the first — factories routinely demo a golden unit and ship variance.

- Record every session; recordings attach to the PO as acceptance evidence and to the Trade Assurance claim file if needed.

- Third-party inspector (SGS/BV/TUV) attends the video FAT in person to verify welds, material thickness and motor nameplates — the things a camera cannot.

# 8. Ordering Schedule (Staged Fleet Delivery)

## Wave 1 — Week 0 (bottleneck + long-lead)

All 6 Fuhe MAP sealers (40 days), both Gondor tunnel ovens (45-60 days), all 7 Kenwei weighers (35 days), Rifu soup fillers x2 and Npack sauce fillers x2 (30 days).

## Wave 2 — Week 3-4 (processing lines)

Beres flakers x2, Vleda dicers x2, Xinlongjia slicer, Dongsheng dicer, Taibo potato line, Longze cookers x6 (CRN paperwork starts here), Crownchi cup lines x4, Leading dryers x2.

## Wave 3 — Week 6-8 (short-lead + balance)

Zhoufeng peelers x2, Saidashi cutter, Fengxiang washers x2, Dayang cutters x2, Vic fruit peeler, Hede kettles x4, JunHong detectors x14. Consolidate by cluster into 10-14 containers landing in a 4-week window.

# 9. Risks & Open Items

- Meal weight & product mix are assumptions. If average meal weight is 350 g instead of 450 g, plant rate drops to ~20,600 kg/hr and several categories lose a unit; if the menu is soup-heavy, cooking capacity doubles. Re-run Section 2 the moment the menu is fixed.

- Utilities & facility: 64 machines draw an estimated 2-4 MW plus steam and refrigeration — confirm Manitoba Hydro service capacity and building design before POs. This is now the project critical path, not the equipment.

- Labour & sanitation: 3-shift operation across 12 packaging lanes implies a workforce plan (est. 300-600 staff) outside this report’s scope.

- Capacity claims: listed rates are manufacturer claims; the sustained full-rate demo protocol (Section 7) is the control. Do not release deposits without recorded rate evidence.

- Supplier concentration: Kenwei carries 7 units across 3 categories — acceptable given their 18-year record, but qualify High Dream (12 yrs) as a certified alternate.

- Freight & install estimates are planning figures — validate with a freight forwarder and a Manitoba millwright contractor before budget approval.

# 10. Recommendations

1. Confirm meal weight, menu mix and pack formats — these drive every machine count in this report.

2. Commission the facility/utilities engineering study (power, steam, refrigeration, effluent) in parallel — it now gates the project.

3. Pre-book SPE-1000 evaluator capacity with Inspection & Technical Services Manitoba for a 64-machine program before releasing any PO.

4. Run the Section 7 virtual viewing program and place Wave 1 (packaging bottleneck) orders first, through Alibaba Trade Assurance only.

5. Use the multi-unit volume (~CA$935K) to negotiate: target 10-20% below listed FOB, extended warranty, 2-year spares, and serial-numbered FATs on every unit.

Prepared by:

Princely Eleazu

AIM Advisors — Project Coordination

Revision 2 — fleet-scale China-direct edition. Supplier data verified on Alibaba.com July 2026; capacity model per Section 2 assumptions.